# POLYTECHNIC UNIVERSITY OF TIRANA

# UNIVERSITY OF TECHNOLOGY OF COMPIÈGNE, FRANCE

# FACULTY OF INFORMATION TECHNOLOGY

# DEPARTMENT OF COMPUTER ENGINEERING

# PROGRESS REPORT — SECOND CONTROL OF THE MASTER THESIS

Thesis title: Uncertainty-Aware Diabetic Retinopathy Grading Using Conformal Prediction and Bayesian Deep Learning

Candidate: Alketa Alia

Supervisor: Prof. Dr. Elinda Kajo Meçe

Submission date: 13/05/2026

Overall status: Approximately 50% complete

## 1. Status summary

The thesis is progressing according to the original plan approved at the First Control. The first experimental phase (binary classification) has been completed with concrete results; the second phase (advanced uncertainty methods) is under active development; the theoretical chapter (Kreu II) is nearly complete, and the methodology (Kreu III) is a first stable draft.

The table below summarises the status by chapter and experimental component.

| Component | Status | Percent |
| --- | --- | --- |
| Kreu I — Introduction | First draft completed | 90% |
| Kreu II — Theoretical Background | First draft, under review | 80% |
| Kreu III — Methodology | Working draft, stabilising | 70% |
| Kreu IV — Phase 1 results (binary) | Experiments completed, tables drafted | 65% |
| Kreu IV — Phase 2 results (UQ) | Implementation in progress | 30% |
| Kreu IV — Phase 3 results (multi-class) | Planned | 0% |
| Kreu V — Conclusions | Planned | 0% |
| Streamlit Application | Functional prototype | 40% |
| Bibliography | 20 current refs, target 40+ | 50% |
| Overall total | — | ~50% |

## 2. What has been done so far

### 2.1 Theoretical part (Kreu I and II)

- The introduction is fully written, with the description of the clinical problem of diabetic retinopathy, the motivation for using uncertainty in medical AI, and the statement of the four research questions that guide the work.

- Kreu II — Theoretical Background — has been written in first draft, including:

  - Pathophysiology and clinical scale of DR (5 stages)

  - APTOS 2019 dataset (3,662 images)

  - Description of the 6 evaluated architectures

  - Concepts of calibration, Monte Carlo Dropout, conformal prediction, and OOD detection

  - Regulatory framework (FDA SaMD, EU AI Act)

### 2.2 Methodology (Kreu III)

- The unified training pipeline has been built (scripts/train.py)

- The stratified 70/15/15 split with fixed random_state has been implemented (scripts/helpers.py)

- Architecture-specific preprocessing for every backbone has been configured

- Standard callbacks are in place: EarlyStopping (patience=10), ReduceLROnPlateau, ModelCheckpoint

- Experimental protocols for calibration, conformal, MCD, and OOD have been documented

### 2.3 Experiments — Phase 1 (binary classification)

Fully completed. Six binary models have been trained, and preliminary results are:

| Model | Test acc | 95% CI |
| --- | --- | --- |
| ResNet50 | 95.27% | [93.45, 97.09] |
| Xception | 95.45% | [93.82, 97.09] |
| DenseNet121 | 95.64% | [94.00, 97.27] |
| VGG16 | 95.64% | [94.00, 97.27] |
| CNN (from scratch) | 96.00% | [94.36, 97.45] |
| CNN (Tanh+ReLU) | 92.91% | [90.72, 94.91] |

Preliminary findings: - The five strong models are statistically indistinguishable (McNemar p > 0.5) - CNN(Tanh+ReLU) is significantly worse (p < 0.05) - The pipeline shows high stability in the reported metrics

### 2.4 Streamlit Application — prototype

A functional prototype has been built (app.py), supporting: - Single image upload - Inference with the selected model - Display of raw probabilities - Multilingual UI (English / Albanian)

## 3. What is currently in progress

### 3.1 Phase 2 — Advanced uncertainty methods

- Conformal prediction (master/uncertainty/conformal.py): LAC implementation is complete; APS and per-class diagnostics are being finalised. Expected to finish within 2 weeks.

- Monte Carlo Dropout: Both variants (cnn_mcd, resnet50_mcd) have been designed; training is in progress. Once trained, T = 30 forward-pass analysis will follow.

- K-Fold Cross-Validation: The script is ready (master/run_kfold_cv.py); execution for ResNet50 is planned (~2 hours on CPU).

- OOD Detection: Implementation of all 4 methods (MSP, Energy, Mahalanobis, Cosine) is in progress.

### 3.2 Statistical analysis

- Bootstrap CI computation is ready and has been executed for Phase 1.

- Pairwise McNemar tests have been executed.

- Calibration analysis (ECE, MCE, reliability diagrams) is half-completed.

### 3.3 Streamlit app expansion

Work in progress to integrate: - Calibrated probabilities (after T-scaling) - Conformal sets in real time - Image-quality heuristics - PDF export

## 4. What remains (~50% remaining)

### 4.1 Remaining experiments

- Full Phase 2: conformal evaluation, MC Dropout analysis, K-Fold CV, OOD detection

- Phase 3 — Multi-class 5-stage grading:

  - Training of cnn_5class and resnet50_5class

  - Quadratic Weighted Kappa, ordinal distance

  - Multi-class conformal with per-class coverage

  - Multi-class calibration

- Classical classifiers (Decision Tree, Random Forest, SVM) on DenseNet features

### 4.2 Remaining writing

- Kreu IV — sections for Phase 2 and Phase 3

- Kreu IV — synthesis of findings and sensitivity analysis

- Kreu V — Conclusions, limitations, and future work

- Abstract in Albanian and English

- Discussion of clinical implications

### 4.3 Supporting components

- Finalisation of the Streamlit application with all UQ features

- Expansion of the bibliography to 40+ references (Vancouver style)

- Creation of all final figures and tables

- Formatting according to the UPT standard (Times New Roman 12pt, 2.54/3.8 cm margins, etc.)

- Table of Contents, List of Figures, List of Tables

## 5. Timeline for completion

| Period | Main activities |
| --- | --- |
| May 2026 (weeks 2-3) | Finalisation of Phase 2: conformal evaluation, MC Dropout, OOD |
| May 2026 (week 4) | K-Fold cross-validation for ResNet50 |
| June 2026 (weeks 1-2) | Training and analysis for Phase 3 (5-class grading) |
| June 2026 (weeks 3-4) | Writing Kreu IV (full results) |
| July 2026 (weeks 1-2) | Writing Kreu V (conclusions) + Kreu IV synthesis |
| July 2026 (weeks 3-4) | Finalising the Streamlit application with all UQ features |
| August 2026 (weeks 1-2) | Bibliography expansion, Kreu II revision |
| August 2026 (weeks 3-4) | Final UPT formatting, TOC + figure/table lists |
| September 2026 (week 1) | Full review with the supervisor |
| September 2026 (week 2) | Final corrections and printing for defence |
| September 2026 (week 3) | Final submission and defence |

## 6. Identified challenges and resolutions

### 6.1 CPU-only training

Challenge: The development environment is CPU-only (MacBook Air M-series, 8 GB RAM). This constrains the architectures and training regimes that are realistically feasible.

Resolution: This has been turned into a methodological point — the system is designed to be deployable in low-resource settings (primary-care clinics). Larger models such as Vision Transformers are left for future work.

### 6.2 Dataset imbalance

Challenge: APTOS has a very skewed distribution (50% No DR, only 13% for stages 3+4 combined).

Resolution: Use of class_weight='balanced' in training; per-class analysis in Phase 3 to surface performance on minority classes; conformal prediction with per-class coverage.

### 6.3 Real OOD validation

Challenge: No second dataset is currently available for cross-dataset evaluation.

Workaround for now: Use of synthetic noise as OOD; the infrastructure for cross-dataset evaluation (master/run_cross_dataset.py) is ready for when Messidor-2 or IDRiD become available.

## 7. Summary statistics

| Indicator | Current value | Final target |
| --- | --- | --- |
| Pages written | ~25 | ~60 |
| Word count | ~8,500 | ≥17,000 |
| Chapters drafted | 3 (Kreu I, II, III) | 5 |
| Result tables | 3 | ~12 |
| Figures | 6 | ~24 |
| Trained models | 6 binary | 10 (6 binary + 2 MCD + 2 multi-class) |
| Bibliography references | 20 | 40+ |

## 8. Conclusion

The thesis is progressing according to the original plan. The first experimental phase has been completed with competitive results (ensemble ~96.5%), and the code infrastructure for the subsequent phases is built and documented. The proposed timeline makes final submission in September 2026 realistically achievable, leaving sufficient time for review with the supervisor and final corrections.

Thank you for your attention and guidance.

Alketa Alia